## Sheet1
Date Range | Tasks
10/02 - 17/02 | • Background Research • Identifying Tech Stack • Project Description and Requirements • Project Structure Setup • Database Design
17/02 - 24/02 | • APIs for login with JWT token, send and verify OTP and reset password • UI for login/authentication, send, verify OTP and reset password and API integration
24/02 - 03/03 | • Dashboard interface based on role - bug reporting and tracking for users to assignment, management, and oversight for developers, testers, team leads, and admins. • API to report a bug with role specific details (browser, device etc for end users and logs, stacktrace for tech users) • UI for bug report submission based on user role and API integration • The system can queue bugs issue type marked as "Other," sending periodic email reminders to team leads and admins until assigned to a team - Optional • Preliminary report • API to list submitted bug reports based on role and team • UI to view list of bugs reported and API integration • API for adding additional information to the submitted bug report • UI to add additional information and API integration
03/03 - 10/03 | • API to assign bug to developer (Team lead/Admin) with email notification to developer • UI for bug assignment and API integration • API to set priority of the bug (Team lead/Admin) • UI for priority setting and API integration • API to update bug status(Open, Fix In Progress, Fixed, Hours worked) by developer, team lead and admin with email notification to reporter • UI for bug status update by developers and API integration
10/03 - 17/03 | • API to add comments to the bug report (only technical users) with email notification to assigned developer • UI for adding comments to the bug report and API Integration • API to assign fixed bug to tester (Team lead/Admin) with email notification to tester • UI for bug assignment and API integration • API to update bug status (Testing In Progress, Verified, Closed, Hours worked) by tester, team lead and admin with email notification to reporter • UI to view bug status update and API integration
17/03 - 24/03 | • Research and finalize the approach/method for duplicate detection. • APIs to detect and store potential duplicates after bug submission • API for fetching and confirming duplicate bugs (Team lead/Admin) • UI to display potential duplicates and allow confirmation
24/03 - 31/03 | • API for filtering, sorting, and searching bug reports • UI for frontend filtering and sorting and API integration • API to reopen closed bugs and roll back status if the fix is incorrect • UI for bug reopening and status rollback • API to request bug reallocation and process approvals • UI for bug reallocation requests and approval workflow • Interim Report
31/03 - 07/04 | • Auto Assign bugs • Research and decide assignment strategy • API for auto-assignment • UI for auto-assignment
07/04 - 14/04 | • Find and preprocess open-source dataset for bug reports with priority labels • Choose the best model to classify priority • Train the machine learning model • API for the trained model • API integration with bug submission process • Implement a rule-based fallback
14/04 - 21/04 | • APIs for fetching role-based analytics such as bug fix rate, bug fixes by priority, team performance etc., • API to export filtered bug reports along with conversion logic • UI for role-based analytics dashboards • Integrate charts and graphs for data visualization • UI to export bug reports with format selection • Export bugs PDF/CSV
21/04 - 28/04 | • Design notification system for real-time updates on bug status, assignments, and approvals • Implement notifications feature • API for storing and fetching unread notifications • UI notification panel to display alerts • Final Report Template • API to mark/unmark a bug as favourite - Optional • API to fetch favourite bugs for a user • UI with a star button to favourite/unfavourite bugs. • UI to display a list of favourite bugs
28/04 - 05/05 | • Research GitHub API for issue creation and status sync - Optional • API to create GitHub issues from reported bugs. • Configure webhook to update BugTrackR when GitHub issue status changes • UI to link/unlink bugs with GitHub issues • Theme switching with Light and Dark modes - Optional • Store user-selected theme & persist across sessions • Implement font customization • UI controls for easy customization
05/05 - 12/04 | • Document Test cases • Testing based on test cases • Bug Fixes • Final Report
12/05 - 19/05 | • Final Report • Preparation for Viva
Date | Milestone | Description
10/02 - 24/02 | Research & Project Setup | Define the tech stack, set up the project structure, and implement authentication with role-based access.
24/02 - 24/03 | Core Bug Reporting & Management | Develop bug reporting, tracking, dashboards, manual assignment, and priority manageament.
24/03 - 07/04 | Advanced Bug Handling | Implement duplicate detection, bug filtering, reallocation requests, and automated bug assignment.
07/04 - 21/04 | ML-Based Enhancements & Role-Based | Integrate ML for priority classification, develop role-based analytics, and enable bug report exports.
21/04 - 05/05 | Notifications & Integrations | Implement email and in-app notifications, integrate GitHub API, and add UI customization.
05/05 - 19/05 | Testing, Optimization & Final Submission | Conduct comprehensive testing, bug fixes, final report submission, and viva preparation.